## Attendance + Contact Details
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Day | Contact No. | TH | F | SA | S | M | T | W | TH | F | SA | S | M | T | W | TH | F | SA | S | M | T | W | TH | F | SA | S | M | T | W | TH | F
Dipesh Thapa Magar |  | 1 TH: WFO; 2 F: WFO; 5 M: WFH; 6 T: WFO
Niraj Maharjan |  | SL | WFH |  |  | WFO | WFH | WFO | WFH | WFO |  |  | WFO | WFO | WFO | WFH | WFO |  |  | WFH | WFO | WFH | WFO | WFO |  |  | WFH | WFO
Sachin Gautam |  | WFH | WFH |  |  | WFH | WFH | WFO | WFH | WFO |  |  | WFO | WFH | WFO | WFH | WFO |  |  | WFH | WFO | WFH | WFO | WFO |  |  | WFH
Sujan Rokaya |  | 1 TH: WFH; 2 F: WFO; 5 M: WFO; 6 T: WFO; 7 W: WFH; 8 TH: WFO; 9 F: WFO; 12 M: SL; 13 T: WFH; 14 W: WFO; 15 TH: WFH; 16 F: WFO; 19 M: WFO; 20 T: WFO; 21 W: WFO; 22 TH: WFO; 23 F: WFO
Index
WO | Week Off
WFO | Work From Office
WFH | Work From Home
SL | Sick Leave
CH | Company Holiday
PTO | Paid Time off

## Alshaya-POC (hidden)
MAY |  | 2023-05-04 |  |  |  | 2023-05-05 |  |  |  | 2023-05-08 |  |  |  |  | 2023-05-09 |  |  |  | 2023-05-10 |  |  |  | 2023-05-11 |  |  |  | 2023-05-12 |  |  |  | 2023-05-15 |  |  |  | 2023-05-16 |  |  |  | 2023-06-01 |  |  |  | 2023-06-02 |  |  |  | 2023-06-05 |  |  |  | 2023-06-06 |  |  |  | 2023-06-07 |  |  |  | 2023-06-08 |  |  |  | 2023-06-09 |  |  |  | 2023-06-12 |  |  |  | 2023-06-13 |  |  |  | 2023-06-14 |  |  |  | 2023-06-15 |  |  |  | 2023-06-16 |  |  |  | 2023-06-19 |  |  |  | 2023-06-20 |  |  |  | 2023-06-21 |  |  |  | 2023-06-22 |  |  |  | 2023-06-23 |  |  |  | 2023-06-26 |  |  |  | 2023-06-27 |  |  |  | 2023-06-28 |  |  |  | 2023-06-29 |  |  |  | 2023-06-30 |  |  |  | 2023-07-03 |  |  |  | 2023-07-04 |  |  |  | 2023-07-05 |  |  |  | 2023-07-06
S.N. | Team Members | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments
1 | Dipesh Thapa Magar | [21 empty] | PTO |  |  |  | PTO |  |  |  | Review on Bealls KT session | In Progress |  |  | Review on Bealls KT session | In Progress |  |  | Install ibm_db module in python 3.10 and change the python script db2 instance | In Progress | 5 |  | Install ibm_db module in python 3.10 and change the python script db2 instance in local testing server | Complete | 4 | Redownload the python3.10. Recompile and configure again and was working | Reconfigure python3.10 and configure required module for connecting ibm_db2 and kafka | Complete | 4 |  | Call with Umair and Ranjith regarding production installation plam | Complete | 1 |  | PTO |  |  |  | Coordinate with Alshaya Azure to allow access to Kibana from jump host | In Progress |  | Forward request to Azure team | Call with Alshaya Azure team for ELK integration demo | Complete
[31 empty] | Sharepoint update for Devops line | In Progress |  |  | Sharepoint update for Devops line | In Progress |  | awaiting approval | Create python script to connect ibm db2 and export result in csv file | Complete | 2 | [9 empty] | Check connection between Azure and IBM prod db and troubleshoot on connecting IBM db2 from python script | Complete | 1
2 | Niraj Maharjan | Analysis on Bealls KT Session and Documents | Complete | 5 |  | ETL KT session for BM |  |  |  |  | Robling Session for BM | Ongoing |  |  | Analysis on Bealls KT Session and Documents | Complete | 5 |  | Research on findings of Bealls session | ongoing | 4 |  | Analysis of Batch monitoring in Bealls | Completed | 4 |  | Job Details of Bealls | Ongoing |  |  | Sick Leave |  |  |  | Review on Bealls KT session | Ongoing | 4 |  | PTO |  |  |  | Kubernetes cluster research | In Progress | 4 |  | ECK on kubernetes | In Progress | 5 |  | ECK on kubernetes | In Progress | 6 |  | kubernetes affinity, resource limit | Complete | 2 |  | ELK PROD Documentation | In Progress | 2 |  | ELK PROD Documentation | In progress |  |  | ELK PROD Documentation | completed |  | Final review pending | 360 review |  | completed |  | ELK setup in local kubernetes cluster | ongoing |  |  | ELK setup in local kubernetes |  | 4 |  | overview of ECK PROD yaml files | In progress | 4 |  | Elasticsearh master node setup and research | In progress | 4 |  | Installed Elasticsearch and kibana on local kubernetes cluster | in progress | 5 |  | Setup Three node elasticsearch | in progress | 4 | Troubleshooting elastic nodes continued | Elasticsearch masternode and client node setup | Complete | 4 |  | Installed and integrated logstash with elasticsearch | complete | 4 |  | installed zookeper in local kubernetes cluster | completed | 4 |  | metricbeat installed in worker node and created dataview and index on kibana | complete | 3 | [5 empty] | Monthly meeting | complete | 2
[11 empty] | Analysis on Bealls KT Session and Documents | ongoing | [6 empty] | Discussion on finding Bealls KT Session | Completed | Scheduled at 2PM |  | Common issues discussion and analysis | Completed | 4 | [9 empty] | Activity Monitor in SSMS | Complete | 4 | [5 empty] | kubernetes engress troubeshooting | In Progress | 4 |  | kubernetes statefull, Deployment | In Progress | 3 |  | Python session |  | 2 |  | Ingress , cert-manager | In Progress | 3 |  | cert-manager, ingress and operator | In Progress | 6 |  | kubernetes operator research | In progress | [6 empty] | system intern interview for two candidates |  | completed |  | Kt session log parsing | complete |  |  | ECK research |  | 4 |  | Writing Elasticsearch Yaml files for locak ELK installation | In progress | 4 |  | Research on three nodes elasticsearch (master,data, and ingest) | In progress | 4 |  | research on volumeclaimtemplates | in progress | 3 |  | Research on volume claim temaplates | in progress | 4 |  | kibana and logstash setup in local kubernetes | Complete | 3 |  | Research on kafka and zookeeper | in progress |  |  | Research on kafka and integration with zookeper | inprogress | 4 |  | logstash pipeline created for system metrics of kubenode1 | complete | 1 | [5 empty] | Troubleshooting kafka and zookeper | complete | 4 |  | cybersecurity for employess slide preparation | in progress | 1
[55 empty] | ECK on kubernetes |  | 3 | [13 empty] | ECK on kubernetes |  | ongoing | [25 empty] | Configuration and test for logstash | in progress | 1 | [9 empty] | Research on zookeper | in progress | 4 | [5 empty] | KAFKA SSL research | complete | 2
3 | Sachin Gautam | [29 empty] | Review on Bealls KT session |  |  |  | Review on Bealls KT session | Ongoing |  |  | call with logic india for updates | completed | 2 |  | call with india logic | completed | 3 |  | troubleshoot kafak and metircbeat issues | complete | 3 |  | pipeline and visualization for oms ( ecom ) | completed | 4 |  | Upgrading local k8s from 1.24 to 1.26 | ongoing | 4 | app deployment left | Call with logic india for changes and update | complete | 4 |  | Visualization of items weeks data | Complete | 4 |  | Call with india team for updates | completed | 2 |  | Call with india team for updates | complete | 2 |  | KT session logstash and parsing | complete | 2 |  | Call with india team for updates | complete | 3 |  | call with logic india for project discussion | complete | 2 |  | changes on ecom dashboard/pipeline | complete | 4 |  | call with logic india team for updates | complete | 3 |  | call with ranjith regarding changes | complete | 2 | KT to pepco team for dashboard and elastic | complete | 4 |  |  | changes on items and picks | complete | 3 |  |  |  |  | Call with india team for some changes
[35 empty] | Power Automate in Jira | Ongoing |  |  | changes on items dashboard | completed | 2 |  | changes on ecom and oms items | ongoing | 5 |  | revert back and pull new changes to elastic of last 2 days | complete | 5 |  | pipeline and visualization for rms-by picks | completed | 4 |  | changes on ecom dashboard | completed | 2 |  | discussion for spaces and DC's dashbaord with india team | complete | 4 |  | changes on HB PO / ASN | complete | 4 |  | KT session to Internal team for dashboard | completed | 2 |  | getting data for all warehouse in one dashboard | ongoing | 3 |  | getting data for all warehouse in one dashboard | complete | 3 |  | changes by -rms picks | complete | 3 |  | KT to internal team for dashbaord | complete | 3 |  | need to diff ecom rms and oms using runtime fields | ongoing | 4 |  | pipeline for by-ils and dashboard | complete | 3 |  | changes for picks for KT with alshaya team | complete | 3 | changes on items | complete |  |  |  | call with shagar and team | complete | 2 |  |  |  |  | data clean up for picks and ecom
[35 empty] | Sharepoint update for Devops line | Ongoing |  |  | pipeline for oms - items | completed | 4 | [25 empty] | changes in picks and pcos | completed | 4 |  | changes in by-rms picks | ongoing | 3 |  | Call with india team for updates | complete | 2 |  | search for sso for elk | ongoing | 2 |  | changes on pick dashboard | complete | 3 | [5 empty] | diff for ecom - rms - ils | ongoing | 2 |  | changes for picks and sales | complete | [6 empty] | changes on sales dashboard | complete | 3 |  |  |  |  | documentation for dashboard update
DY Roster Management
4 | Sujan Rokaya | [29 empty] | PTO |  |  |  | PTO |  |  |  | Kubernetes (Deployment, Statefulset ,Volumes) | In Progress | 5 |  | AWS and terraform | In Progress | 5 |  | ECK on kubernetes | in Progress | 4 |  | ECK on kubernetes | in Progress | 2 |  | Ingress , cert-manager | In progress | 6 |  | cert-manager | In Progress | 4 |  | kubernetes (cert-manager | In progress | 2 |  | SL |  |  |  | ECK on kubernetes | In Progress | 3 |  | Logparsing | complete | 4 | had filebeat error and solved | Elasticsearch (ILM policies ) | in Progress | 2 |  | Elasicsearch data nodes | In progress | 3 |  | Elasticsearch and kibana SSO | In progress | 3 |  | ECK on kubernetes | in progress | 6 |  | ECk on kubernetes (logstash integration ) | in progress | 3 | . further debugging required | Integration of Kafka and filebeat | Complete | 4 | solved certificate problems and send the logs from filebeat to kafka topics | call with team | complete | 1 |  | kubernetes Role, Cluster role, Role binding | in progress | 2 |  | kubernetes RBAC[Role Based Access Control ] (Cluster Role, Role Binding , Service account ) | in progress | 4 | configuration for providing certain access to external users in kubernetes cluster | kubernetes RBAC | completed | 7 | created a role such that only a namespace is accessible to a user with limited permission over a cluster | KAFKA SASL | in progress | 5 | integrating kafka broker and client with SASL protocol. kafka is running as a single entity but is not able to send and recieve messages through topics. | Kafka SASL | in progress | 5 | getting error in connection of kafka clients and broker , | Kafka SASL integration | in progress | 5 | error in connection of kafka and zookeeper . producer and consumer are not working . | kubernetes volumes, pvc , dynamic provision ... configured yaml files for ECK | completed | 5 | configured all yaml file ready to be deployed in local storage | debugging of kubernetes cluster onRHEL 8 | in progress | 6 | the cluster formed on rhel was very unstable. on each access to the VM the connection was closed to cluster and kubernetes component like coredns , kubelet were not working properly
[39 empty] | Grafana | In Progress | 3 |  | Kubenetes (Volumes , Statefulset ) | In Progress | 3 |  | Kubernetes Volume | in Progress | 2 |  | Python session | in Progress | 2 |  | ECK on kuberetes ( operator ) | In progress | 2 |  | kibana and grafana documentation | In Progress | 1.5 |  | ECK on kubernetes | in Progress | 5 | [5 empty] | Filebeat | In Progress | 2 |  | Kt session log parsing | in progress | 1 |  | Dashboard documentation | in Progress | 4 |  | Dashboard documentation | Complete | 4 |  | Kubernetes ( configmap ,yaml manifest ) | In progress | 3 |  | integrating logstash in ECK | in progress | 2 |  | integrating kafka and filebeat | in progress | 5 | certificate issues | Elasticsearch multiple nodes ( master, data , ingest ) along with kibana integration | in progress | 4 | kibana service not available .port unavailable . Further debugging going on | elastic and kibana integration | in progress | 3 | kibana service is not reachable inside servers minikube . | Kafka Topic issue | in progress | 6 | sending logs from metricbeat to kafka topic but the logs are not being sent , However the connection is maintained . error in broker client and replication factor issues . | Debugging with Sandhya D for kubernetes cluster setup using kubeadm | in progress | 1 | no internet access to some certain links for setup so could not complete the setup | Kafka with SASL | in progress | 1 | Sasl in another security protocol for kafka clients and broker that uses username and password | Kt session by sachin dai | complete | 1 |  | Kubernetes cluster kubeadm | completed | 1 | revision on how to make kubernetes cluster and make master node usable for pod deployment | demo setup of kubernetes cluster along with ECK | in progress | 3 | helping sandhya didi setup kubernetes cluster with kubeadm along with ECK using operators | setup of kubernetes cluster and ECK deployment | in progress | 3 | due to crio faced many problem leading to unstable kubernetes cluster revert back to containerd instead of CRIO | trying to setup k8 cluster on RHEL 9 | completed | 2 | same issue were found as of RHEL 8
[47 empty] | Kubernetes Cluster with containerd | Complete | 2 |  | [TLS/SSL, CA, PKI ] | in Progress | 4 | [5 empty] | python session | In Progress | 2.5 |  | Kibana | In progress | 1 | [5 empty] | logstash parsing | In Progress | 3 |  | Elasticsearch [ ILM ] | in progress | 1 |  | ECK multiple data nodes | in progress | 2 | [5 empty] | Snapshot and Recovery | In progress | 2 | [13 empty] | logstash integration with ECK pipelines | complete | 2 | index in elasticsearch are formed. |  |  |  |  | ECK setup with kafka and metricbeat | complete | 3 | data are sent from metricbeat to kafka then to logstash and to elasticsearch. |  |  |  |  | Monthly meeting | complete | 1.5 |  | Elasticsearch , logstash | completed | 2 | revison on grok patterns and pipeline creation
[75 empty] | ECK on kubernetes | in progress | 2

## Alshaya-POC-JULY (hidden)
MAY |  | 2023-05-04 |  |  |  | 2023-05-05 |  |  |  | 2023-05-08 |  |  |  |  | 2023-05-09 |  |  |  | 2023-05-10 |  |  |  | 2023-05-11 |  |  |  | 2023-05-12 |  |  |  | 2023-05-15 |  |  |  | 2023-05-16 |  |  |  | 2023-07-03 |  |  |  | 2023-07-04 |  |  |  | 2023-07-05 |  |  |  | 2023-07-06 |  |  |  | 2023-07-07 |  |  |  | 2023-07-10 |  |  |  | 2023-07-11 |  |  |  | 2023-07-12 |  |  |  | 2023-06-13 |  |  |  | 2023-07-14 |  |  |  | 2023-07-15 |  |  |  | 2023-07-16 |  |  |  | 2023-07-17 |  |  |  | 2023-07-18 |  |  |  | 2023-07-19 |  |  |  | 2023-07-20 |  |  |  | 7/212023 |  |  |  | 2023-07-24 |  |  |  | 2023-07-25 |  |  |  | 2023-07-26 |  |  |  | 2023-07-27 |  |  |  | 2023-07-28 |  |  |  | 2023-07-31
S.N. | Team Members | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments
1 | Dipesh Thapa Magar | [21 empty] | PTO |  |  |  | PTO |  |  |  | Review on Bealls KT session | In Progress |  |  | Review on Bealls KT session | In Progress | [66 empty] | Work on elastic data migration from UAT to PROD | completed |  |  | Preapration of elastic data migration from UAT to PROD | Ongoing |  |  | Finalize the documentation for elastic data migration from UAT to PROD and shared to team | Completed |  |  | Follow up with elastic support team for ELK licensing | Completed |  |  | Prepare timelien for production deployment and migration timeline | Completed |  |  | Call with Umair for Production deployment and migration timeline | completed
[103 empty] | Preapration of elastic data migration from UAT to PROD | Ongoing |  |  | Alshaya standup | completed |  |  | Alshaya Standup | Completed |  |  | Project overview and Kt session for team | Completed
[31 empty] | Sharepoint update for Devops line | In Progress |  |  | Sharepoint update for Devops line | In Progress |  | awaiting approval | [68 empty] | Follow with elastic support for licensing details | completed |  | Will schedule call after we fixed the country from where we are going to purchase license
2 | Niraj Maharjan | Analysis on Bealls KT Session and Documents | Complete | 5 |  | ETL KT session for BM |  |  |  |  | Robling Session for BM | Ongoing |  |  | Analysis on Bealls KT Session and Documents | Complete | 5 |  | Research on findings of Bealls session | ongoing | 4 |  | Analysis of Batch monitoring in Bealls | Completed | 4 |  | Job Details of Bealls | Ongoing |  |  | Sick Leave |  |  |  | Review on Bealls KT session | Ongoing | 4 | [5 empty] | changes in ecom dashboard | Complete | 2 |  | Call with logic india team for dashboad modification | Complete | 1 |  | Troubleshooting kubernetes cluster setup in redhat | Complete | 3 |  | troubleshooting kubernetes cluster setup in RHEL 8 ElK setup in kubernetes cluster | Complete | 5 |  | changes in all metricbeat query timings | Complete | 2 | [49 empty] | call with logic india team for project updates | Completed
[11 empty] | Analysis on Bealls KT Session and Documents | ongoing | [6 empty] | Discussion on finding Bealls KT Session | Completed | Scheduled at 2PM |  | Common issues discussion and analysis | Completed | 4 | [9 empty] | Activity Monitor in SSMS | Complete | 4 | [5 empty] | kubernetes RnD | In Progress | 5 | volumclaim templates | changes in items summary dashboad | Complete | 3 |  | changes in alshaya items details dashboard | Complete | 1 |  | changes in items summary and items details dashbaord | Complete | 2 |  | changes in ecom,picks and pco dashboard and troubleshooing filebeat issues | Complete | 2 |  | Dashboard query timing documentation as reqested by logic india | completed | 3 |  | Troubleshooting dashboard data mis match | inprogress | 3 |  | Changes on Dashboard, due to mismatch data | completed | 3 |  | Research on RBAC kubernetes | in progress | 5 | [9 empty] | Troubleshooting data mismatch in kibana | in progress | 4 |  | Read only user created in kubernetes using RBAC | completed | 4 |  | Troubleshooting shards error | inprogress | 4 |  | Troubleshooting Kibana dashboard issues on ILS ERROR | inprogress | 4 | [5 empty] | Alshaya standup | completed | 1 |  | Documentation of ELK dashboard work flow | in progress |  |  | Dashboard Config and modification | completed | 4 |  | Automation for query execution in SIOCS system | in progress | 4 |  | Automation for query execution in SIOCS system | in progress | 4 |  | Trouble shooting double data show in kibana due to logstash pipeline error | in progress | 4
[43 empty] | cybersecurity for employees | In Progress | 1 | [5 empty] | call with alshaya team regarding dashboard changes | Complete | 1 |  | document server details and other details requested by logic india | Complete | 1 |  | Second half leave |  | 4 |  | Research on RBAC | inprogress | 4 |  | dynamic volume research in kubernetes | inprogress | 5 |  | Research on Rbac Kubernetes | in progress | 5 |  | Troubleshooting RBAC on local kubernetes | in progress | 3 | [9 empty] | Creating user in kubernetes using RBAC | in progress | 4 |  | kubernetes cluster troubleshooting | completed | 4 |  | Kibana troubleshooting for dashboard not loading properly | inprogress | 4 |  | Researh on Kibana circuit breaker issue | inprogress | 3 | [5 empty] | call with logic india team for troubleshoting dashboatd issues | in progress | 2 | [5 empty] | ELk data flow documentation | completed | 3 |  | dashbord data mismatch troubleshooting | in progress | 3 |  | Dashboard modification and data validation | in progress | 4 |  | Second half leave |  | 4
[51 empty] | kubernetes RBAC research | In Progress | 3 | [9 empty] | Cybersecurity for employess slides review | completed | 1 | [33 empty] | Metricbeat ,Filebeat KT session | completed | 1 | [5 empty] | Troubleshooting kubernetes cluster issue | in progress | 5 | [5 empty] | call with logic india team | completed | 1 |  | call with team for project discussion | Completed | 1
4 | Sujan Rokaya | [29 empty] | PTO |  |  |  | PTO | [7 empty] | kubernetes volumes, pvc , dynamic provision ... configured yaml files for ECK | completed | 5 | configured all yaml file ready to be deployed in local storage | debugging of kubernetes cluster onRHEL 8 | in progress | 6 | the cluster formed on rhel was very unstable. on each access to the VM the connection was closed to cluster and kubernetes component like coredns , kubelet were not working properly | setup kubernetes cluster with one worker node on RHEL 8 | completed | 6 | faced various issues of CNI used (flannel ) . setup cluster using containerd | kubernetes cluster setup in RHEL 8 ElK setup in kubernetes cluster | completed | 8 |  | kubernetes ingress | in progress | 3 |  | Elasticsearch ILM | in progress | 5 | transition of data in different phases ( hot, warm , cold and frozen ) | Elasticsearch ilm for data retention | in progress | 3 |  | Elasticsearch ILM, Warm,cold,frozen architecture | in progress | 5 | transition of index in different phases | Elasticsearch Data nodes , ILM | in progress | 5 | [9 empty] | Elasticsearch ILM | in progress | 2 |  | configuration of ELk with multiple data nodes and thier dynamic volume provison | completed | 2 | [5 empty] | Elasticsearch snapshot and restore | in progress | 5 | snapshot taken and restored in local setup using local storage , now planning for storinf snapshot in azure cloud. | Backup documentation | completed | 2 |  | Logstash configuration | completed | 6 | data from logstash were not going to elasticsearch . dead instance error. solved it by redeploying cluster | Log parsing | in progress | 5 | multiple line logs so they need to be converted into filebeat multiline pattern and then parsed. logs are pasred but not in suitable format | [12 empty] | logstash csv file | in progress | 4 | csv parse failure and data dublicate error. debugging
[43 empty] | setup of kubernetes cluster and ECK deployment | In Progress | 3 | due to crio faced many problem leading to unstable kubernetes cluster revert back to containerd instead of CRIO | trying to setup k8 cluster on RHEL 9 | completed | 2 | same issue were found as of RHEL 8 | kubernetes pv and pvc | in progress | 2 | [5 empty] | elasticsearch logstash and filebeat configuration | Complete | 3 | shards full issue in a cluster. | Kubernetes | in progress | 3 |  | Kubernetes ingress | complete | 5 | applied ingress in local kubernetes cluster. | kubernetes cluster confiuration ( Test ) | in progress | 3 | configuration of elastic nodes with additional role for warm and cold phases | Kubenetes configuration | in progress | 3 | changes some of services into nodeport . demo of kubernets cluster, logstash to sandhya D | [8 empty] | Kubernetes dyanmic volume provision in local setup using openebs | completed | 6 | testing of dynamic volume provision on local kubernetes setup completed. manual creation of pv and pvc not required | Metricbeat, kafka, | completed | 4 | had error while sending logs from the pipeline.solved the issue a | Filebeat kafka logstash configuration for csv file | completed | 3 | faced issue in zookeeper and kafka. | Metricbeat ,Filebeat KT session | completed | 1 | kt session of filebeat and metricbeat configuration | Elasticsearch ( Shards, Reindexing | completed | 5 | max doc shard can store , best practices and planning on how to reindex the existing data for minimizing elastic shards and load on cluster | Log parsing | in progress | 2 | logs are parsed but suitable result is not obtained . further debugging for exact values | Kubernetes configuration | Completed | 3 | due to error in logstash filter part, index were not created in elasticsearch.debugged and completed . | Logparsing for RIB | in progress | 5 | in filebeat, configuration of multiline pattern is resulting in error. proper result is not achieved. | Log Parsing | in progress | 6 |  | Log parsing for poison | completed | 6 |  | Log parsing for Adapters | completed | 2
[59 empty] | Metricbeat documentation | in progress | 2 | [29 empty] | kubernetes | in progress | 2 |  | Metricbeat configuration | completed | 3 |  | Backup documentation |  | 2 |  | Kubernetes debugging | completed | 1 | debugging with cluster setup for palash dai . | [8 empty] | Snapshot and Restore in azure Blob test | complete | 3 | configured repository in azure for storing snapshot and restoring them. | Kibana Dashboard | in progress | 2 |  | Log parsing for Adapters | in progress | 2 |  | call with india team | completed | 1
[95 empty] | research on Azure disk for pvc provision | in progress | 2 | [29 empty] | KT Session about Cluster to Prabesh dai | in progress | 1

## Alshaya-POC-AUGUST (hidden)
AUGUST |  | 2023-08-01 |  |  |  | 2023-08-02 |  |  |  | 2023-08-03 |  |  |  | 2023-08-04 |  |  |  | 2023-08-07 |  |  |  | 2023-08-08 |  |  |  | 2023-08-09 |  |  |  | 2023-08-10 |  |  |  | 2023-08-11 |  |  |  | 2023-08-14 |  |  |  | 2023-08-15 |  |  |  | 2023-08-16 |  |  |  | 2023-08-17 |  |  |  | 2023-08-18 |  |  |  | 2023-08-21 |  |  |  | 2023-08-22 |  |  |  | 2023-08-23 |  |  |  | 2023-08-24 |  |  |  | 2023-08-25 |  |  |  | 2023-08-28 |  |  |  | 2023-08-29 |  |  |  | 2023-08-30
S.N. | Team Members | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments
1 | Dipesh Thapa Magar | Call with Elastic support | Complete |  |  | troubleshoot picks and pco's dashboard | Complete |  | Recreate the scenario in the logic elk system. No issue exist. Review the logs and was issue on python scripts. | Daily standup call with Alshaya PM | Complete |  |  | Call with Account director for elastic licensing | Complete | [6 empty] | Call with Alshaya ILS to discuss regarding to integrate their system | Complete |  |  | Move dashboar of ILS GRN and ADJ to new separate space | Complete |  |  | Debugging issue for reindexing | Complete |  |  | Call with ranjith for configuring beat agents manually | Complete |  |  | elasticdump for remaining error index while reindexing | completed |  |  | Create Summary view dashboard for pco | Complete |  |  | Call with Alshaya team for prod vm provisioning | Complete |  |  | Troubleshoot on UAT ELK stack. | Complete |  |  | Call with Alshaya team for listing UAT ELK set up challenges | Complete |  |  | Call with Alshaya Azure team for Prod provision status | Complete | [10 empty] | Follow up with elastic support team for elastic image vunerability | Complete |  |  | Follow up with elastic support team for elastic image vunerability | Complete |  |  | Production ELK stack deployment | In Progress |  |  | Kafka deployment in PROD | Complete |  |  | Troubleshoot on creating snapshot repository in UAT and PROD | Complete
|  | Call with Alshaya for VM server Planning | Complete |  |  | Call with Nandhini and Umair for estimating hour for migration | Complete |  |  | Verify the grok pattern to parse the log for NVENTORY ADJ and GRN - ILS | Complete |  |  | Call for August release plan and legacy dashboard | Complete | [6 empty] | Elastic data reindexing | In Progress |  | Troubelshoot on reindexing. Dashboard showing incorrect data after indexing | Call with ILS team to gather information what can be implemented | Complete | [6 empty] | Configure filebeat in Retail batch server | Complete |  |  | dashboard modification for GRN and ADJ | completed | [10 empty] | Call with Alshaya team for listing UAT ELK set up challenges | In Progress |  |  | Daily stand up call | Complete |  |  | Follow up with elastic support team for elastic image vunerabilties | Complete | [14 empty] | Call with Alshaya team for pod povision | Complete |  |  | Troubleshoot on prod depoyment | Complete |  |  | Troubleshoot on creating snapshot repository in UAT and PROD | In Progress |  |  | Call with Alshaya team deployment and migration status | Complete
[14 empty] | Prepare plan for reindexing and draft document. Send for approval | Complete | [10 empty] | Call with logic indian team to gather requirement to ceate legacy dashboard | Complete | [6 empty] | GRN/ADJ dashboard demo | Complete |  |  | verfify index for Legacy dashboard | completed | [34 empty] | Show and tell session | Complete |  |  | Call with Alshaya team regarding PROD steup status | Complete |  |  | Call with Alshaya team for data mgration timeline | Complete |  |  | Troubleshoot on create indexing in ELK UAT | Complete
|  | troubleshoot picks and pco's dashboard | In Progress |  | Duplicate data in ILS_BRAND. Recreate the scenario in local server and foud no issues | Call with Alshaya team for New VM in PROD Approach | Complete |  | After getting the approval with respective team the ELK provisioning will start by Alshaya cloud team | [72 empty] | Call with Alshaya team for PT and Volume test planning | Complete
2 | Niraj Maharjan | troubleshoot picks and pco's dashboard | In Progress |  | Duplicate data in Pco-aLL dashboard | call with team for project updates and discussion |  |  |  | Research on kibana dashboard optimization and performance improve | In Progress |  |  | Kibana dashboard and query optimization research | In Progress |  |  | Research on kibana dashboard optimization and query management | In Progress | 4 |  | Documentation for kibana optimization | Complete | 2 | sent for review to logic india team | Research on kibana legacy dashboard creation | In Progress |  |  | Research on MSSQL integration with metricbeat | In Progress | 4 |  | Troubleshooting data not loading in kibana | In Progress | 2 |  | Research on fleet server and elatic agent | in progress |  |  | legacy dashboard overview by dipesh dai |  |  |  | Troubleshooting data not loading in kibana | In Progress | 3 | [25 empty] | configure metricbeat to query on DASRECON db | Complete |  |  | Troubleshooting dashdb on sit index not creating | In Progress |  | query logs can be seen in kafka but index are not created. Pipelines seems to be fine | Pipeline creation for new dashdb queries | Complete |  |  | troublesooting logstash configuratio and kafka logs not created in topics
|  | call with team for project discussion | Complete |  |  | troubleshoot picks and pco's dashboard | Complete |  | Issue was due to running old and new scripts that was causing duplicate data | call with logic team | Complete |  |  | call with logic team for project updates and discussion | Complete |  |  | Testing and Troubleshooting metricbeat installation on MSSQL server | In Progress | 4 |  | call with logic team for project updates | Complete | 1 |  | call with logic india team for project status and discussion | Complete |  |  | call with logic team | Complete | 1 |  | Call with ranjith for configuring beat agents manually | Complete | 1 |  | call with logic team | completed |  |  | call with logic team |  |  |  | call with logic india team for updates | Complete | 1 | [5 empty] | Trouble shooting dashboard data mis match | Complete | 6 |  | Overview of python script to extract data | In Progress |  |  | System dashboard creation for azure vm using metrcis | Complete | 3 |  | Configure metricbeat for configuring pipelines and executing new query in das recon db | In Progress | 4 | [5 empty] | Troubleshooting index on created for DASHRECON DB Queries | In Progress | [6 empty] | metricbeat configuration and scheduled queries | Complete |  |  | call with logic team for updates
[14 empty] | kibana dashboard data validation and troubleshooting | Complete | [6 empty] | call with alshaya team for oracle clinet and metricebat installation | Complete | 1 | metricbeat stopped currently, need to change the db query in metricbeat | Research on ELK license procedure | Complete |  |  | Research on Elastic agent and Fleet server | In Progress | 3 |  | call with logic india team for project discussions and updates | Complete | 1 | [5 empty] | metricbeat & filebeat installation documentation |  |  |  | Setup local instance of Fleet server and elastic agent | In Progress | 4 | executing mssql query successful, now need to research on creating daily index |  |  |  |  | call with logic team for project discussion | Complete | 1 |  | call with shaul regarding pyhton script KT | Complete |  |  | call with logic team for updates | Complete | 1 |  | call with shahul regarding SITDASRECON db connection issue and query not running | Complete | 1 |  | Troubleshooting dasrecon db index not creating | In Progress |  |  | call with logic team for updates | Complete | [6 empty] | Call with Alshaya team for PT and Volume test planning | Complete
[22 empty] | Research on metricbeat intergration on MSSQL server 2016 | Complete | 4 | successfully executed query and sent outpu to kibana | [8 empty] | Researach on Fleet server and elastic agent | In Progress | 4 | [17 empty] | call with logic team for python script walk through | Complete | 1 |  | call with logic team for project updates | Complete |  |  | Test python script on local environment to load data from source db to dest db | In Progress | 4 |  | Research on kibana dashboard issue regarding number of data limit | In Progress | 3 |  | call with logic team for updates | Complete
4 | Sujan Rokaya | Log parsing for rib poison and adapters | In Progress | 5 | completed for poison | log parsing for alsaya new log | In Progress | 5 | writing conditional grok | log parsing for alsaya new log | Complete | 6 | parsed multiple line of given log file, configuration of filebeat and logstash pipeline ,waiting for ranjith to provide further instruction | ILM testing and Reindexing test | Complete | 4 | Test successful and created a plan for reindexing with Dipesh dai | Research on Folder monitoring using beats agent | In Progress | 4 | tried monitoring from metricbeat module system [process] , confifigured heartbeat for monitoring but appropriate result was not obtained. could not monitor from beats agent | Elastic data reindexing | Complete | 8 | converting daily time-series index into monthly index for proper data management | Elastic reindexing | In Progress | 7 |  | elastic data reindexing | In Progress | 7 |  | cluster debuging for pepco | Complete | 1 | configured pipeline [ filebeat>> kafka>> logstash ] | Elasticsearch combining 2 index | in progress | 5 | team decided to write script and generate a combined index .no need to do in elasticsearch | elastic dump for recovering back index | Complete | 4 |  | kubernetes Volume Expansion | In Progress | 4 | testing in progress | kubernetes volume expansion | In Progress | 2 | testing in hold | Research on Azure CNI | In Progress | 4 |  | call with shaul regarding pyhton script KT | In Progress | 3 | script that moves table from one database to another in loop | Test python script on local environment to load data from source db to dest db | In Progress | 7 |  | python script regarding data transfer between two databases | In Progress | 4 | discussion with shahul regarding configuration of python script for some changes. | python script regarding data transfer between two databases | Complete | 5 | one script ended with error and one successfull | call with logic team | Complete | 1 |  | Prod Setup in Alshaya through call | In Progress | 8 | only kafka remaining due to lack of certificates | Prod setup of ELK cluster Through call | Complete | 8 |  | Setup Blob repository in Azure for Elastic Snapshot Through call | Complete | 8 | Snapshot taken and restored for 3 months of data . April, May , June
|  | call with logic india | Complete | 1 |  | call with logic india team | Complete | 1 |  | call with logic team | Complete | 1 |  | call with logic team | Complete | 1 | [13 empty] | call with logic team | Complete | 1 |  | elastic data reindexing | Complete | 5 |  | elasticdump for remaining error index while reindexing | completed | 2 |  | call with logic team | Complete | 1 |  | kubernetes cluster debugging | Complete | 3 | pipelines were not working so debugged and solved it | kubernetes cluster debugging | Complete | 5 | pod was not being scheduled after a restart.found the issue and solved it | call with logic team | Complete | 1 |  | debuging kubernetes cluster | Complete | 3 |  | call with logic team for updates | Complete | 1 |  | call with logic team | Complete | 1 |  | call with logic team | Complete | 1 |  | kubernetes Volume Research (PV and PVC) | Complete | 5
|  | csv error | In Progress | 2 | logstash is unable to parse csv files .>> malformed csv error | ILM research and draft | Complete | 2 | created a simple ILm policy and created a draft for the process | ILM policy | In Progress | 1 | testing in progress for existing data to move through different phases | Cluster Upgrading Test | Complete | 3 | upgrading ELK cluster of 8.2.3 to 8.8.1 without any data loss in local environment | Research on ILM on daily time series indexx | In Progress | 4 | [5 empty] | call with team | Complete | 1 | [5 empty] | elastic Rollup jobs | In Progress | 2 |  | call with logic team | completed | 1 |  | kubernetes Volume [ increasing existing pvc for pods ] | In Progress | 3 |  | call with logic team | Complete | 1 |  | call with logic team | Complete | 1 |  | prepare yam file for production | In Progress | 3 |  | kubernetes Volume Expansion | Complete | 2 | size of pvc bound to a pod can be increased without any data loss. |  |  |  |  | local kubernetes cluster configuration | Complete | 3 |  | kubernetes Volume Research (PV and PVC) | In Progress | 2 |  | Elasticserach Enterprise Liscence trial | In Progress | 2
5 | Prabesh Baniya | Configure and Troubleshoot CSV parsing in Logstash | Complete | 3 |  | Study Grok Patterns | Complete | 3 |  | Parse logs provided by Ranjit using Grok and Regex | Complete | 4 |  | Further study on log parsing, conditional statements | Complete | 2 |  | Study on ILM and reindexing | Complete | 1 |  | Install Elasticsearch on Kubernetes cluster and further study on indexing | In Progress | 2 |  | Sick Leave |  |  |  | Study Indexes, shards, clusters, nodes in elastic search | In Progress | 2 |  | Study Indexes, shards, clusters, nodes in elastic search | Complete | 4 |  | Setup elastic search and add records for indexing | in progress | 2 | [13 empty] | Discussion with Nandhini regarding python scripting | Complete |  |  | Call with Shahul for walkthrough of the python script used for moving data accross different databases | Complete | 3 | [5 empty] | Leave |  |  |  | Research and work on python script to transfer data between two databases | Complete | 3 |  | Look into metricbeat to send query to dasrecon and pipelines in logstash to receive query from kafka | In Progress | 3 |  | Look into metricbeat to send query to dasrecon | Complete | 2
|  | Study Grok Patterns | In Progress | 1 |  | Parse logs provided by Ranjit using Grok and Regex | In Progress | 1 | [5 empty] | Study on ILM and reindexing | In Progress | 1 |  | Install Elasticsearch on Kubernetes cluster and further study on indexing | In Progress | 3 | [57 empty] | Look into pipelines in logstash for creating indices | In Progress | 2

## Alshaya-POC-September (hidden)
SEPTEMBER |  | 2023-09-01 |  |  |  | 2023-09-04 |  |  |  | 2023-09-05 |  |  |  | 2023-09-06 |  |  |  | 2023-09-07 |  |  |  | 2023-09-08 |  |  |  | 2023-09-11 |  |  |  | 2023-09-12 |  |  |  | 2023-09-13 |  |  |  | 2023-09-14 |  |  |  | 2023-09-15 |  |  |  | 2023-09-16 |  |  |  | 2023-09-17 |  |  |  | 2023-09-18 |  |  |  | 2023-09-19 |  |  |  | 2023-09-20 |  |  |  | 2023-09-21 |  |  |  | 2023-09-22 |  |  |  | 2023-09-25 |  |  |  | 2023-09-26 |  |  |  | 2023-09-27 |  |  |  | 2023-09-28 |  |  |  | 2023-09-29
S.N. | Team Members | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments
1 | Dipesh Thapa Magar | Follow with Elastic team for elastic image vunerabilties fixed for patches release for version 8.8.1 | Complete |  |  | Follow with Elastic team for elastic image vunerabilities | Complete |  |  | Dashboard export/Import from UAT to PROD | Complete |  |  | Increase elastic data pvc in UAT | Complete | [10 empty] | Alshaya daily standup call | Complete |  |  | Alshaya daily stand up call | Complete |  |  | Alshaya daily stand up call | Complete |  |  | Alshaya daily stand up call | completed |  |  | Alshaya daily stand up call | Complete | [10 empty] | Alshaya Daily standup call | Complete |  |  | Alshaya Daily standup call | Complete | [6 empty] | Alshaya Daily standup call | Complete |  |  | Alshsya daily standup call | Complete |  |  | Alshaya Daily standup call | Complete |  |  | Alshaya Daily standup call | Complete |  |  | Alshaya daily stand up call | Complete |  |  | Alshaya daily stand up call | Complete | Complete |  | Alshaya daily stand up call | Complete
|  | Call with Alshaya team for prod migration | Complete |  |  | Call with Alshaya team for prod migration | Complete |  |  | Call with Alshaya team for prod migration status | Complete |  |  | Call with Alshaya team for PROD migration status | Complete | [10 empty] | Call with Alshaya PM for production migration status | Complete |  |  | Coordinate with Alshaya Azure team for uploding elk images 8.9.1 to repository | Complete |  |  | Oracle instant client configutration in Azure PROD VM | Complete |  |  | Filebeat and metricbeat installation/configuration in PROD Azure VM | completed |  |  | Coordinate with Alshaya Azure team to access prod AKS cluster through AD and test the log sending to prod kafka | Complete | [10 empty] | Call with Alshaya team regarding the docker image vunerabilities | Complete |  |  | Call with Alshaya team regarding the production migration status | Complete | [6 empty] | Research on installing enhanced table plugin in Kibana | Complete |  |  | Create dashboard in local kibana through enhanced table plugin | Complete |  |  | Call with Alshaya team regarding the data migration status | Complete |  |  | Troubleshoot on conifiguring enhanced table plugin in UAT | Complete |  |  |  | Complete |  |  | Install python packages in prod Azure VM | Complete |  |  | Internal call to validate the KT dashboard | Complete
[14 empty] | Call with Pedro regarding issue for dashboar | Complete | [10 empty] | Discussion with Alshaya team for using ELK version 8.9.2 | Complete | [26 empty] | Deploy elk version 8.9.1 in PROD | Complete | [26 empty] | Enhanced table plugin configured in UAT ELK | Complete |  |  | Enhanced table plugin configured in PROD ELK | Complete |  |  | Change in dashboard after internal review | Complete
[86 empty] | Deploy license in ELK prod | Complete |  |  | Internal call for reviewing production plan status | Complete
2 | Niraj Maharjan | Dashboard creation for items completed | Complete | 4 | need review by logic india team | Dashborad creation for adjustment queries |  |  |  | Dashboard modification for new items query | Complete | 4 |  | call with logic india team for troubleshooting ELK stack and kubernetes |  |  |  | hnm log dashboard creation | Complete |  |  | call with alshaya team for demo of metricbeat/ filebeat for hnm log parsing | Complete |  |  | new query added for ils reconcilation | Complete | [14 empty] | troubleshooting logstash pipelines | Complete |  |  | data pipelines created for ecom dashboard AMAP-95 | Complete |  |  | Dash board completed for ecom | Complete |  | need review by india team | meticbeat configuration and query scheduling |  |  |  | Meritcbeat configuration |  |  |  | Dashboard creation for PICKS/PCO | In Progress |  |  | Dashboard creation for PICKS/PCO | In Progress |  |  | Dashboard creationg for items | In Progress | [6 empty] | Leave |  |  |  | Leave |  |  |  | Leave |  |  |  | ASn monitoring data pipelines created | Complete | 2
|  | troubleshooting logstash configuration issues as index were not being created | Complete | 3 | isssue resolved after redeploying logstash | call with logic team for updates |  |  |  | call with logic team for project updates | Complete | 1 |  | call with logic team for project updates |  |  |  | call with logic team for updates | Complete |  |  | troubleshooing hnm log dashboard creation | Complete |  |  | Linux training slides creation for TU | In Progress | [10 empty] | call with logic team for updates | completed |  |  | call with logic team for updates | Complete |  |  | call with logic team for updates | Complete |  |  | call with genco regarding dashboards | Complete |  |  | Data pipeline and Dashboard creation for items |  |  |  | Data pipelines creation for PICKS/PCO |  |  | data pipelines completed index creation remaining | call with logic team for updates | Complete |  |  | call with logic team for updates | Complete |  |  | call with logic team for updates | Complete | [18 empty] | ASN monitoring query scheduled in metricbeat and dashboard creation | Complete | 5
|  | call with logic team for updates | Complete | 1 | daily standup |  |  |  |  | Troubleshooting kibana dashboard errors | Complete | 3 |  | Research and troubleshooting kibana issues | [11 empty] | table structure dashboard creation for ils reconcilation | Complete | [22 empty] | call with logic team for updates | Complete | [10 empty] | System intern interview |  |  |  | call with logic team for kibana troubleshooting | Complete |  |  | Troublehshooting dashboard creation for percentage value of items | In Progress | [18 empty] | call with logic team | Complete | 1
K
4 | Sujan Rokaya | Elk Prod setup | In Progress | 8 | elk cluster setup in prod environment kafka remaining | Elk Cluster setup | Complete | 8 | Setup kafka and configuration of ELK cluster ,troubleshooting | Configuration of Repository in Azure Blob for Snapshot | Complete | 4 |  | Snapshot restore in Prod environment | Complete | 2 |  | log parsing of hnm logs | Complete | 4 | log parsing and dashboard |  |  |  |  | Re-indexing August Indices in UAT | In Progress | 8 |  | Reindexing of August indices and Snapshot and Restore | Complete | 5 |  | Elasticsearch troubleshoot | Complete | 4 | shards failure issue | Elasticsearch local cluster troubleshoot | completed | 5 |  | Troubleshooting UAT cluster | In Progress | 5 | indices are not created | Data pipeine anad sample dashboard creation | Complete | 6 |  | Dashboard creation fr GRN | In Progress | 8 | changes in dashboard according to genco. troubleshooting. | Data pipeline and Dashboard optimization | In Progress | 8 | dashboard optimization going on | Troubleshooting Dashboard for GRN, PICKS and ITEMS | In Progress | 7 | dashboard for GRN, picks and Items KPI | Troubleshooting Table panel for Dashboard in kibana | In Progress | 7 | troubleshooting changing values into percentage. | Kibana Enhanced table plugin Integration | In Progress | 4 | plugin for kibana for better visaulization . integration and troubleshooting | Interation of Kibana Plugin in ELK stack | Complete | 3 | enhanced table plugin | Log Parsing for Error log Job status | Complete | 4 |  | Dashboard creation for Error log job status | In Progress | 6 | had error in filebeat and solved th issue. | Dashboard creation for Error log Job status | Complete | 5 | call with logic india team for changes and additional configuraiton for folder containing logs | Dashboard creation fo GRN,PIcks | In Progress | 5 | table creation using enhanced table plugin. exploring plugin | Dashboard creation fo GRN,PIcks | Complete | 3 | table creation using enhanced table plugin.
[10 empty] | Snapshot and Reindexing in UAT environment | Complete | 4 |  | Reindexing in UAT and PROD | In Progress | 6 |  | Reindexing | Complete | 4 | [9 empty] | Testing of logstash pipeline | Complete | 3 |  | ArgoCD | In Progress | 4 | deploying in local kubernetes cluster from git | Metricbeat and Logstash pipeline | completed | 3 |  | Troubleshooting Metricbeat | Complete | 3 |  | Troubleshoot in data pipelines | Complete | 2 | [9 empty] | call with logic team | Complete | 1 |  | call with logic team | Complete | 1 | about dashboard changes and modification. | Grok parsing for new log | Complete | 4 | need to configure pipelines and dashboard in UAT |  |  |  |  | Troubleshooting Data pipelines for Error log job status | Complete | 4 |  | Troubleshooting in Uat cluster for Enhanced tab;e plugin | Complete | 2 | tested locally , need to do in UAT | Dashboard creation fo GRN,PIcks | In Progress | 2 | table creation using enhanced table plugin. exploring plugin | Troubleshooting For Dashboard % value | Complete | 2 |  | Reindexing and Snapshot restore in UAT | In Progress | 4
[82 empty] | call with logic team | Complete | 1 | for updatea and changes in configuration | call with logic team | Complete | 1 | for updatea and changes in configuration | call with logic team | Complete | 1 | for updatea and changes in configuration
5 | Prabesh Baniya

## Alshaya-POC-October (hidden)
OCTOBER |  | 2023-10-02 |  |  |  | 2023-10-03 |  |  |  | 2023-10-04 |  |  |  | 2023-10-05 |  |  |  | 2023-10-06 |  |  |  | 2023-10-09 |  |  |  | 2023-10-10 |  |  |  | 2023-10-11 |  |  |  | 2023-10-12 |  |  |  | 2023-10-13 |  |  |  | 2023-10-16 |  |  |  | 2023-10-17 |  |  |  | 2023-10-18 |  |  |  | 2023-10-19 |  |  |  | 2023-10-20 |  |  |  | 2023-10-26 |  |  |  | 2023-10-27 |  |  |  | 2023-10-30 |  |  |  | 2023-10-31
S.N. | Team Members | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments
1 | Dipesh Thapa Magar | Alshaya Daily standup call | Complete |  |  | Alshaya Daily standup call | Complete |  |  | Alshaya Daily standup call | Complete |  |  | Alshaya Daily Standup Call | Complete |  |  | Alshaya Daily standup Call | Complete |  |  | Alshaya Daily standup call | Complete |  |  | Alshaya Daily standup call | Complete |  |  | Alshaya Daily standup call | Complete | [6 empty] | Alshaya Daily standup call | Complete | [30 empty] | Daily stand up call with Alshaya team | Complete
|  | Coordinate with Alshaya team regarding Azure storage account access | Complete |  |  | Troubleshoot on logstash pipeline in PROD ELK | Complete |  |  | Logstash deployment for new change in PROD | Complete |  |  | Migrate dashboard from UAT to PROD | Complete |  |  | Observability weekyl stand up call | Complete | [6 empty] | Research on iintegrating audit log for kibana | In Progress |  |  | Filebeat installation and configuration of HB PO ASN logs | Complete | [6 empty] | Production Dashboard Issues Support | Complete | [30 empty] | GRN - Daily Reconciliation 3PL deployment in prod | Complete
[10 empty] | Migrate logstash pipeline from UAT to PROD | Complete |  |  | UAT to PROD migration status call | Complete | [14 empty] | Production Dashboard Issues Support | Complete | [6 empty] | Logic Internal weekly meeting | Complete
[38 empty] | CAB document for configuring Audit log in production | Complete
2 | Niraj Maharjan | dashboard modification and optimization for picks and pco monitorings | Complete |  |  | dashboard modification for pco and picks | Complete |  |  | logstash pipeline creation for adjustments and items | Complete |  |  | dashboard creation for items and adjustments | Complete | [10 empty] | datapiple line creation and meticbeat configuration for 3pl queries | Complete |  |  | troubleshooting pco monitoring queries | Complete |  |  | Dashboard creation for picks monitoring query | In Progress |  |  | dashboard modification for PICKs monitoring | Complete |  |  | data pipelinecreation and query scheduling on metricbeat for adjustment monitoring | In Progress |  |  | dashboard creationg for adjustment monitoring quries | Complete |  |  | 3PL GRN dashboard creation | In Progress |  |  | 3PL GRN dashboard creation | Complete |  |  | KT session to Vishnu for data pipeline and Dashboard creation | Complete |  |  | PTO |  |  |  | 3PL Dashboard creation for ASN | Complete |  |  | call with alshaya team for PROD Dashboard fixes | Complete |  |  | call with logic team for updates | Complete
|  | call with logic team for updates | Complete |  |  | call with logic team for updates | Complete |  |  | call with alshaya for team kt session for pick and pco dashboards | Complete |  |  | call with alshaya team for KT session on Iterms and adjustment dashboad | Complete | [6 empty] | call with logic team for updates | Complete |  |  | call with team for feedback review | Complete |  |  | call with logic team | Complete |  |  | call with logic team for updates | Complete |  |  | call with logic team for updates | Complete |  |  | call with logic team for updates | Complete |  |  | call with logic team for updates | Complete |  |  | call with logic team for updates | Complete |  |  | call with logic team for updates | Complete |  |  | call with logic team for updates | Complete | [6 empty] | call withh logic team for updates | Complete |  |  | Dashboard documentation for PROD Deployment | Complete |  |  | cybersecurity mock sessions | Complete
|  | query scheduling and meticbeat configuration for picks and pco monitorings | Complete | [22 empty] | dashboard creation for 3PL queries | Complete | [30 empty] | Data pipeline creation for 3PL | [15 empty] | 3PL ASN moroco dashboard creations | Complete
3 | Sujan Rokaya | Reindexing for remaining indices of September | Complete | 5 |  | Snapshot and restore of indices up to October | Complete | 3 | up to october 3 |  |  |  |  | Logstash from ECK operator | In Progress | 5 |  | Logstash deployment for centralized pipeline | In Progress | 5 | [21 empty] | integration for Kibana audit logs | In Progress | 6 | issue while integrating sidecar container for kibana | Dashboard modification for all monitoring queries | Complete | 7 | review from ITOPs remaining | Integration of new HB logs ( log parsing data pipelines and Dashboard | In Progress | 6 |  | HB LOGS Data pipeline and Dashboard | Complete | 5 |  | KT session to Vishnu for data pipeline and Dashboard creation | Complete | 1 |  | Modification of HB logs Dashboard | Complete | 2 | Dashboard Changes for AME | Dashboard issuess in HB PO & ASN | In Progress | 3 |  | PROD deployment of HB logs | Complete | 6 |  | PROD Dashboard fixes for ASN and AdJustment monitoring queries | In Progress | 4 | the updated queries seems to have some issues
|  | Work ethics meeting by HR | Complete | 1 |  | Logstash deployment | In Progress | 5 | deploying logstash from ECK operator in Prod |  |  |  |  | Logstash config migration from UAT to PROD | Complete | 3 |  | data restore form UAT to prod till october 6 | complete | 3 |  | Research on Kibana plugins for better visaulization | In Progress | 6 | interation of plugins with kibana image and deployment to kubernetes cluster | Kibana User activity Tracker | In Progress | 6 |  | Integration of filebeat module of kibana audit log | In Progress | 7 | for kibana user monitoring. facing errorsa | created a sample dashboard for user activity in local ELK cluster | In Progress | 5 | optimization and modification required | Dashboard modification for PICKs monitoring | Complete | 2 |  | Dashboard modification | Complete | 2 |  | call with team | Complete | 1 |  | Dashboard modification for GRN monitoring | Complete | 2 |  | call with logic team for updates | Complete | 1 | review from genco to change all the queries and dashboard modification to be done | Modification of queries in all the data pipelines | In Progress | 5 |  | integration of New queries for 3pl | Complete | 5 | the queries were later need to be reverted because of usecase | PROD Deployment of 3PL Picks Recon | Complete | 5 |  | call with alshaya team for PROD Dashboard fixes | Complete | 2 |  | Dashboard fixes in UAT for 3pl HB PO & ASN Recon | In Progress | 2 | 3pl QTy and RMS qty are not matching . query issue
|  | Elasticsearch new Liscence Walkthrough | In Progress | 2 | [17 empty] | call with logic team | Complete | 1 | [5 empty] | call with logic team | Complete | 1 |  | Dashboard optimization for ITEM POC | Complete | 3 |  | Kibana Audit log | In Progress | 6 | [17 empty] | HB Logs Dashboard modification | Complete | 2 |  | call with logic team for updates and changes | Complete | 1 | [9 empty] | call with logic team for updates | Complete | 2
4 | Prabesh Baniya

## Alshaya-POC-November (hidden)
NOVEMBER |  | 2023-11-01 |  |  |  | 2023-11-02 |  |  |  | 2023-11-03 |  |  |  | 2023-11-06 |  |  |  | 2023-11-07 |  |  |  | 2023-11-08 |  |  |  | 2023-11-09 |  |  |  | 2023-11-10 |  |  |  | 2023-11-20 |  |  |  | 2023-11-21 |  |  |  | 2023-11-22 |  |  |  | 2023-11-23 |  |  |  | 2023-11-24 |  |  |  | 2023-11-25 |  |  |  | 2023-11-27 |  |  |  | 2023-11-27 |  |  |  | 2023-11-28 |  |  |  | 2023-11-29 |  |  |  | 2023-11-30 |  |  |  | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05
S.N. | Team Members | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Hours Spent | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments
1 | Dipesh Thapa Magar
2 | Niraj Maharjan | Troubleshooting 3PL pco dashboard | In Progress |  |  | Troubleshooting 3PL PCO dashboard | Complete |  |  | dashboard modification for PCO monitoring queries | Complete |  |  | Troubleshooting dashboards for GRN monitoring queries |  |  |  | Dashbord creation for RMS ARES | Complete |  |  | Dashboard modification and customizations | Complete |  |  | dashboard documentation for RMS -ARES reconcilation | Complete
|  | call with logic team for updates | Complete |  |  | call with logic team for updates | Complete |  |  | call with logic team for updates | Complete |  |  | call with logic team for updates |  |  |  | datapipelines creation for RMS ARES and metricbeat configuration | Complete |  |  | call with team for dashboard issue and fixes | Complete |  |  | call with logic team for updates | Complete
|  | change 3PL PCO queries and schedule metricbeat | Complete |  |  | call with logic team for troubleshooting 3PL Queries and dashboard modification | Complete
3 | Sujan Rokaya | Dashboard fixes for ASN and AdJustment monitoring queries | In Progress | 4 | debugging for null and empty values | PROD Deployment of HB PO ASN Dashboard | Complete | 3 | metricbeat configuration and data pipelines in logstash |  |  |  |  | solved open issues raised by ITOPs team | Complete | 8 | only GRN is remanining , need updated query from india team | dashboard modification in adjustment monitoring queries | Complete | 3 |  | Query change in asn monitoring and grn monitoring | Complete | 3 |  | changing the query time of all monitoring queries and 3Pl queries in PROd in metricbeat | Complete | 3 | time set to 11 30 |  |  |  |  | Data pipelines for Ecom Sales returns | Complete | 3 |  | Troubleshooting ecom OMS RMS dashboard for null values | In Progress | 3 |  | scheduling queries for ECOM ILS Recon dashboard, data pipelines and dashboard creation | Complete | 4 |  | Dashboard fixes in prod for Adjustment monitoring and PCo monitoring | Complete | 3 |  | Ecom ILS kpi query schedule , data pipeline and dashboard creation | Complete | 3 | [5 empty] | data pipelines for ecom oms resa and dashboard creation | In Progress | 4 |  | RMS_ARES Item [panel added] | Complete |  | complete | RMS_GRN Reconcilation | complete |  |  | Dashboard fixes for Ecom OMS RMS | complete | 4 |  | RMS-ARES-GRN recon GRN MONITORING PROD fixes | Complete
|  | Dashboard fixes for HB PO ASN | In Progress | 3 | debugging for null and empty values | Dashboard fixes for HB PO ASN, PICKS Dashboard | Complete | 4 | fixing null value problem in kibana with scripted fields | [8 empty] | call with team |  | 1 |  | Dashboard modification |  | 4 |  | Dashboard Modification | Complete | 3 | adding extraction time |  |  |  |  | Dashboard validation for Ecom sales | In Progress | 4 | null values need to be fixed | prod dashboard fixes for GRN monitoring queries | Complete | 3 |  | added a panel in RMS-ARES Item Reconcilation | Complete | 3 |  | Changin queries and dashboard creation of all ECOM Header panels | Complete | 3 |  | Dashboard fixes for Ecom Header level and Detail level dashboard | In Progress | 4 | count in db and elastic is not matching |  |  |  |  | dashboard fixes for rms ares item reconcilation | Complete | 3 |  | ECOM OMS RESA | In Progress |  | validation pending | ECOM OMS ILS KPI Dashboard fixes | complete |  |  | troubleshooting | complete | 3 |  | call with logic team isuue tracker | Complete | 2
|  | call with logic team for updates | Complete | 1 |  | call with logic team | Complete | 1 | [9 empty] | troubleshoting and dashboard validation |  | 4 |  | call with team for dashboard issue and fixes |  | 1 | [9 empty] | call with team | Complete | 1 |  | call with team regarding issues | Complete | 2 |  | call with logic team | Complete | 1 |  | call with logic team | Complete | 2 |  | call with team | Complete | 2 | [5 empty] | call with logic team | Complete | 1 |  | call with team | Complete | 1 |  | KT Session Alshaya | complete | 1 |  | KT Session Alshaya | complete | 1 |  | PROD dashboard fixes for 3pl RMS GRN, ASN
4 | Prabesh Baniya | [64 empty] | call with team | Complete | 1 | [5 empty] | KT session

## Alshaya-December (hidden)
December |  | 2023-12-01 |  |  |  | 2023-12-04 |  |  |  | 2023-12-05 |  |  |  | 2023-12-06 |  |  |  | 2023-12-07 |  |  |  | 2023-12-11 |  |  |  | 2023-12-12 |  |  |  | 2023-12-13 |  |  |  | 2023-12-14 |  |  |  | 2023-12-15 |  |  |  | 2023-12-16 |  |  |  | 2023-12-17 |  |  |  | 2023-12-18 |  |  |  | 2023-12-19 |  |  |  | 2023-12-20 |  |  |  | 2023-12-21 |  |  |  | 2023-12-22 |  |  |  | 2023-12-23 |  |  |  | 2023-12-21 |  |  |  | 2023-12-22 | 2023-12-23 | 2023-12-24 | 2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-12-30 | 2023-12-31
S.N. | Team Members | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Hours Spent | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments
1 | Dipesh Thapa Magar
3 | Sujan Rokaya | ProD dashboard fixes for 3pl GRN reconn | Complete |  |  | Ibal Stock reconcilation Dashboard fixes |  |  | max bucket issue adding controls to filter and show data based on brand and warehouse | Troubleshooting iBal Stock Reconcilation | In Progress |  |  | Prod Dashboard fixes | Complete |  | adding today filter to all 3pl and monitoring dashboard | Prod Deployment of ECOM OMS RMS Recon |  |  |  | Prod Dashboard reload for GRN MONITORING QUERIES | Complete |  |  | 3PL GRN RECON STRATEGIC METRIC | Complete |  | schedule metricbeat, data pipelines and dashboard creation in UAT | PROD DEPLOYMENT OF ECOM Intra Country Picks OMS/RMS PROD DEPLOYMENT | Complete |  |  | rescheduling query in PROD from 11:30 am to 9:am | Complete |  |  | Unrealised sales Metric Views | Complete |  | schedule metricbeat, data pipelines and dashboard creation in UAT | [8 empty] | PROD deployment of HB Files Monitor | Complete |  |  | 3pl query refreshed at 10:50 AM IST | Complete
|  | HB_hen Dashboard in UAT scheduling queries , data pipelines and dashboard | Complete | [6 empty] | Ecom OMS RESA Dashboard query change for sales panel | In Progress |  | data more than 300k cannot be reflected in kibana[max bucket size limit ] | ECOM OMS RESA Sales Header |  |  |  | Inegration for ECOM KPI Intra country |  |  |  | Refreshing ECOM OMS RMS RECON | Complete |  |  | dashboard documentation | In Progress |  |  | filter removal in prod dashboard | Complete |  |  | Dashboard refresh for ASN monitoring queries | Complete |  |  | call with elastic support | Complete | [10 empty] | 3PL GRN Recon panel fix | Complete |  |  | 3PL GRN Strategic panel fix | Complete
|  | Troubleshooting ECOM ILS KPI % panel in UAT | In Progress | [6 empty] | call with logic team | Complete | 1 | [9 empty] | Dashboard fixes for ECOM OMS RESA and deployment to PROD | Complete |  | updated the detail view panel with new query | Prod Dashboard fixes | Complete |  | reloading ASN monitoring queries Dashboard | call with logic team | Complete |  |  | KT to sabil |  |  |  | KT to sabil | [15 empty] | Dashboard Documentation | Complete
|  | call with logic team | Complete | 1 | [5 empty] | Prod dasboard fixes | In Progress |  | adding today filter | [36 empty] | call with team | Complete
3 | Sabil Shrestha

## Jan
December |  | 2024-01-01 |  |  |  | 2024-01-02 |  |  |  | 2024-01-03 |  |  |  | 2024-01-04 |  |  |  | 2024-01-05 |  |  |  | 2024-01-08 |  |  |  | 2024-01-09 |  |  |  | 2023-12-13 |  |  |  | 2023-12-14 |  |  |  | 2023-12-15 |  |  |  | 2023-12-16 |  |  |  | 2023-12-17 |  |  |  | 2023-12-18 |  |  |  | 2023-12-19 |  |  |  | 2023-12-20 |  |  |  | 2023-12-21 |  |  |  | 2023-12-22 |  |  |  | 2023-12-23 |  |  |  | 2023-12-21 |  |  |  | 2023-12-22 | 2023-12-23 | 2023-12-24 | 2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-12-30 | 2023-12-31
S.N. | Team Members | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Hours Spent | Task Details | Task Status | Hours Spent | Comments | Task Details | Task Status | Hours Spent | Comments
1 | Dipesh Thapa Magar
2 | Sabil Shrestha

## Action_Items & Announcement
S.N | Start Date | Task | Details | Owner | Completed Date | Active Days | Status | Comment | Links
1 | 2023-07-26 | Snapshot and Restore | Documentation and test in local environment | Sujan/Dipesh |  | 5 | Completed
2 | 2023-07-28 | Troubleshoot on picks and pco's dashboard | Data duplication. Manually import data in local system and its working. | Niraj/Dipesh | 2023-08-02 | 3 | Completed | 8/1 -Recreate the scenario in the logic elk system. No issue exist. 8/2- Review the logs and there was issue on python scripts. The old python scrpts was running. The dtat will be verified on 8/3
3 | 2023-07-31 | Follow with Alshaya support team for VPN issue | The password has been reset for prabesh,niraj and sujan but can't login in MFA | Dipesh | 2023-08-30 | 2 | Completed | 7/31 - The credential create was not working. 8/1- Recreate the ticket zendesk for ogin issue
4 | 2023-08-01 | Document on ILM polciy requirement |  | Dipesh |  |  | Completed | 8/1 - Document already shared in Jira ticket
5 | 2023-08-02 | Log parsing of client sample file for HB log |  | Sujan | 2023-08-02 | 2 | Completed | 8/3 logs parsing completed and send the data format to Ranjith. Waiting for client response
6 | 2023-08-03 | Optimize the dashboard performance | List down way how we can optimize the dashboard in elk system | Niraj | 2023-08-08 | 5 | Completed | 8/3 list the parameter and configuration 8/8 forward the document to Ranjith
7 | 2023-08-03 | Log parsing INVENTORY ADJ and GRN - ILS File Transfer Logs | Send the parse log to elastic inorder to create the dashboard | Dipesh |  | 2 | Completed | 8/2 - Gather requirement from Nandhini what needs to be visualize in dashboard 8/3 - Verify the grok pattern to parse the log- Completed 8/4 - configuring logs location in filebeat, creating Logstash pipeline and create dashboard - next task 8/4 - Dashboard created and wating for review | Dashboard
8 | 2023-08-03 | Elastic rollover job | Recreating mutiple indexes into single
9 | 2023-08-04 | Reindexing elastic index on UAT | We are increasing shards count every week. We need to provide the solution for it | Dipesh/Sujan |  | 7 | Completed | 8/4 - prepare reindexing plan and present to Shirley for approval- provided document to Umair 8/7 - will be start reindexing after getting approval 8/8 - Start reindexing in UAT 8/8: 20 indices has been reidexed 8/9: troubleshoot on reindexing issue(data validation issue) 8/10: reindex 146 indices 8/11: reindexing completed 8/14: dump 4 error indices and upload in sharepoint 8/15: restore dump indices in local ELK 8.8.1
10 | 2023-08-14 | GRN/ADJ dashboard modification. | Change in dashboard as per feedback | Dipesh | 2023-08-18 |  | Completed | 8/11: Add table structure for success and failed
11 | 2023-08-21 | Elastic images vunerabilties | Many vunerabilties seen in elastic image 8.8.1 and 8.2.3. Follow up with elastic team for stable image | Dipesh | 2023-08-24 |  | Completed | 8/21: Email sent to elastic support team regarding vunerabilties and ask for stable images 8/24 Alshaya agreed to use elasti image version 8.8.1
12 | 2023-08-23 | Configure metricbeat and create pipelines and dashboard for new queries on be executed on SIT DASRECON DB | completed metricbeat configuration and creation of pipelines | Niraj |  |  | completed | index creation issue, need to create dashboard once data is loaded in elasticsearch.
13 | 2023-08-28 | ELK Deployment |  | Sujan/Dipesh | 2023-08-30 |  | Completed | 8/28 elastic/kibana/logstash zookeeper Deployment completed 8/28 Troubleshoot on Deployment 8/29 Kafka Deployment completed 8/29 Troubleshooting on create snapshot repository in PROD and UAT 8/29 Create snapshot repository in PROD
14 | September 1,2023 | Dasboard creation for items/picks/adjustments | Dashboard creation for items completed | Niraj |  | 1 | Completed | 9/1 completed dashboard for items needs review by india team
15 | September 4,2023 | Reindexing elastic index on UAT up to july |  | Sujan | 2023-08-05 | 2 | completed
16 | Septembet 6, 2023 | Snapshot in UAT and Restore in PROD | data migrated till july | Sujan | 2023-08-07 | 2 | completed
17 | Septembet 11, 2023 | Reindexing August Elastic Indices In UAT and Snapshot and Restore in Prod |  | Sujan | 2023-08-12 | 2 | completed
18 | September 14,2023 | Dashboard creation for pco, items and GRN | logstash pipelines for all of these has been completed | Niraj |  | 2 | completed | Issue in creating kibana index, troubleshooting logstash, and kafka still not able to resolve this issue
19 | Sepetember 18,2023 | Dashboard creation for Picks monitoring | There out of 4 dashboard completed . need to troubleshoot one of the dashboard for percentage | Niraj/Sujan |  |  | completed
20 | Sepetember 20,2023 | Dashboard creation for PCO monitoring | All dashboard completed only one remaining | Niraj |  |  | completed
21 | September 21 2023 | Dashboard creation for Ecom | All dashboard completed | Niraj/Prabesh | 2023-09-23 | 3 | Completed | dashboard completed. need review by india team
22 | 2023-09-26 | Dashboard Creation for Error Log Job Status | Data pipelines and dashboard for Error log Job status have been completed | Sujan/Dipesh | 2023-09-26 | 2 | completed
23 | 2023-09-27 | Integration of plugin for kibana in Kubernets cluster for both UAT AND PROD | created a new custom image for kibana and updated the kubernetes cluster | Sujan/Dipesh | 2023-09-27 | 2 | completed | exploring new added plugins for dashboard requirement
24 | 2023-09-27 | Dashboard Creation for GRN,PCO and PICKs | Percenatage value shown in kibana table using enhanced table kibana plugin | Sujan/Dipesh | 2023-09-29 | 3 | completed
25 | September 28. 2023 | Integration of Liscence for ECK in PROD | integraiion of Enterprise liscence | Dipesh | 2023-09-28
26 | 2023-09-29 | Dashboard and Data pipeline for ASN Monitoring queries | Dashboard for ASN Monitoring | Niraj | 2023-09-29 | 1 | Completed | dashboard completed. need review by india team
27 | September 29,2023 | Dashboard creation for ASN Monitoring | Created three table structure dashboard for ASN | Niraj | 2023-10-02 | 2 | Completed | dashboard completed. need review by india team
28 | OCtober 4 ,2023 | KT session on picks and pco monitoring for alshaya team |  | Niraj | 2023-10-04 | 1 | Completed | made few changes on picks and pco monitoring
29 | OCtober 5 ,2023 | KT session on Adjustments and items monitoring for alshaya team |  | Niraj | 2023-10-05 | 1 | Completed | made few changes on items and adjustment monitoring after review by logic india team
30 | OCtober 10 ,2023 | Audit logs in Kibana | Capture user activities | Dipesh/Sujan |  |  | In progess
31 | OCtober 10 ,2023 | Dashbaord creation for sample 3pl queries | 2 table structure dashboard created | Niraj | 2023-10-10 | 1 | Completed | sample dasboard created. new dashbaords for 3pl will be created once we receive new queries for it
32 | OCtober 9 ,2023 | Dashboard documentation for august ans september |  | Niraj | 2023-10-10 | 2 | Completed
33 | October 10 ,2023 | Change dashboard as per feedback |  | Dipesh/Niraj/Sujan |  |  | Completed
34 | October 13 ,2023 | Prepare CAB Document for redeployment of Kibana Audit logs in Production |  | Dipesh | October 13 ,2023 | 1 | Completed
35 | October 17,2023 | Dashboard modification for GRN,ITEM,PCO,Adjustment ,PICKs and ITEMS monitoring queries | adding extraction time in all the existing table | Sujan | October 17,2023 | 1 | completed | review left by IT ops team
36 | October 17,2023 | Data pipelines and Dashboard creation for new queries for 3pl RMS picks recon | Data pipelines and Dashboard have been made for revuew | Niraj |  |  |  | Data Type Error in some field
37 | October 17,2023 | HB FTP logs integration with filebeat | Data pipelines and Dashboard have been made for revuew | Sujan | 2023-10-18 | 2 | completed
38 | 2023-10-20 | Modification of queries in PROD | For ASN, PICKS, ADJ, GRN and ITEMS monitoring | Dipesh | 2023-10-20 | 1 | Completed | Old queries replaced with Updated queires
39 | October 27.2023 | Dashboard Documentaion | documentation for 3pl dashboards | Niraj |  | 2 | completed
40 | October 27.2023 | Deployment of 3pl Picks Recon in Prod | Data pipelines and Dashboard have been made in prod | Sujan | October 27,2023 | 1 | completed
41 | October 30,2023 | Deployment of HB logs Dashboard | Data pipelines and Dashboard have been made in prod | Sujan | 2023-10-30 | 1 | Completed
42 | 2023-10-30 | Deployment of 3pl GRN Recon | Data pipelines and Dashboard have been made in prod | Dipesh | 2023-10-30 | 1 | Completed
43 | 2023-10-31 | Dashboard issue in oman-detailed-level-metric-GRN | Elastic is taking null value as 0001-01-01 . | Dipesh | 2023-11-01 | 1 | Ongoing | for now leave date with NULL value
44 | 2023-10-31 | Dashboard issue in oman-detailed-level-metric-GRN | Required column( 3pl_qty and RMS_qty ) missing in elastic | Sujan | 2023-11-02 | 1 | Completed
45 | 2023-10-31 | Data pipelines and Dashboard creation for morocco 3PL ASN | issue on one of the queries sent by logic india | Niraj |  | 1 | Completed | one of the dashboard creation completed
46 | 2023-10-31 | Dashboard issue | due to NULL value in column accurdate data was not showing in dashboard | Dipesh | 2023-11-01 | 1 | Completed | 11/1-Call with Genco and logic india team 11/2- Conclusion was to modified the query
47 | 2023-11-01 | Update queries and dashboard migration from ASN/GRN/Picks/PCOs | due to NULL value in column accurdate data was not showing in dashboard | Dipesh/Sujan/Niraj | 2023-11-03 | 3 | Completed | 11/1- Queries change in ASN/GRN 11/2- Dashboard modification for GRN/ASN 11/2- Dashboard validate and migrated to Prod 11/2- query update and dashboard modificateion for Picks and PCOs 11/3- Validate dashboard by logic india team | ASN/GRN migration deadline NOV1 >> move to Nov2 - completed Picks/Pcos migration deadline Nov2 >> move to Nov3 - Dashboard validation ogoing by Logic india team
48 | 2023-11-01 | Data Mismatch | There was the two data field in elastic index and showing the incorect data due to NUL value and numeric alphabet data | Dipesh/Sujan/Niraj | 2023-11-03 | 2 | Completed | 11/2 - Create new scripted filed in elastic data view to megre two filed for ASN/GRN 11/2 - 11/2 - Create new scripted filed in elastic data view to megre two filed for Picks/PCOs
49 | 2023-11-03 | Automate dashboard mail sending | For new dashboards automate them to send via email (Genco's request - Stuart | Vishnu |  | 1 | Ongoing | 11/7- smtp conifguration left > need to request Alshaya team to provide smp details
50 | 2023-11-06 | Dashboard modification for Picks | Dashboard validated by Baskar. Dashboard data is not matching with dashboard | Dipesh/Sujan/Niraj |  | 1 | Completed | 11/8- Queries shared by baskar
51 | 2023-11-06 | All montoring dashboard modification | Modify all monitoring dashboard (PCO/ASN/GRN) | Dipesh/Niraj/Sujan |  |  | Completed | 11/7- PCO Monitoriing - 3 out of 4 issue resolved 11/7 - GRN Monitoring - 4 out of 8 issue resloved 11/7 - Picks Monitoring - 3 out of 3 issue resloved 11/7 - ASN Monitoring - 4 out of 4 issue resloved "
52 | 2023-11-07 | PICK NUM and DISTRO NUM vlaute not matching with dashboard | Number value (3048708460) is taking as 3.04870846e+09. | Dipesh |  | 1 | Completed | 11/8 Import table structure and table data in local database 11/8 Troubleshott on running sql query through metricbeat in local environment
53 | 2023-11-07 | Datapipelines and dashboard creation for ILS RMS Stock Reconciliation ILS ARES Stock Reconciliation | created one table structure dashboard | Niraj | 2023-11-08 | 1 | Completed | 11/7- Schedule queries in metricbeat 11/7- Create data pipeline 11/7 - Create dashboard and handover for validation
54 | 2023-11-08 | Query change for ASN and GRN monitoring | created a table view for each dashboards |  | 2023-11-08 |  | Completed | Validation left from India team
55 | 2023-11-08 | ASN Morocco processed and unprocesed query change and dashboard modification |  | Dipesh/Niraj/Sujan | 2023-11-08 |  | Completed | 11/8 - Query modification in UAT 11/8 - Dashboard modification in UAT 11/8 - dahsboard verification by logic india team 11/8 - Query change and dashboard import in PROD
56 | 2023-11-08 | KT session issue | Dashboard modification as per feedback | Sujan | 2023-11-08 |  | Completed | 11/8 - ASN Monitoring 11/8 - GRN Monitoring
57 | 2023-11-08 | Create dashboard for HNM logs in PROD |  | Dipesh | 2023-11-08 |  | Completed | 11/8 - Add logs file location in filebeat 11/8 - Create dashboard HNM logs in PROD
58 | 2023-11-09 | Dashboard documenation | Dashboard documentation completed for RMS-ARES, ITEMS | Niraj | 2023-11-09 | 1 | completed | 11/9 STOCK iBal Sample File Testing ITEMS - Daily Reconciliation RMS-ARES (Qualitative checks GRN - Daily Reconciliation ARES - RMS
59 | 2023-11-16 | Dashboard modification | - Panel names to be changed - remove distro num column as its duplicate of pick num - insert dates need to remove - pick_date column name rename to 3PL create date - distro type to remove as its duplicate of order type - tot_pick_qty rename to 3PL_qty - Quantity rename to rms_qty | Dipesh | 2023-11-16 | 1 | Completed | 11/16 - Change don 3PL Picks
60 | 2023-11-16 | Dashboard modification for GRN/ASN/PCO | - Panel names to be changed - remove distro num column as its duplicate of pick num - insert dates need to remove - pick_date column name rename to 3PL create date - distro type to remove as its duplicate of order type - tot_pick_qty rename to 3PL_qty - Quantity rename to rms_qty | Dipesh | 2023-11-16 |  | Completed | 11/17 - required changes done in PROD dashboard
61 | 2023-11-16 | Data validation ARES GRN Reconciliation | Dashboard data is not matching with database data | Dipesh | 2023-11-16 | 1 | Completed | 11/17 - ares_qty column having null and change the query in metricbeat
62 | 2023-11-16 | Data validation ILS RMS Stock for Reconciliation dashboard | Dashboard data is not matching with database data | Dipesh |  |  | Completed
63 | 2023-11-16 | Data validation for HB log | Dashboard is not showing logs generated in HB logs file | Dipesh | 2023-11-21 |  | Completed
64 | 2023-11-17 | ARES GRN Reconciliation migration in PROD | Move query/data pipeline/dashboard in PROD |  | 2023-11-17 |  | Completed | 11/17- Migration completed in PROD
65 | 2023-11-20 | ECOM OMS-RMS RECON | Schedule query/ create data pipeline and dashboard | Sujan |  |  | Completed | due to null value some columns are not being reflected in elastic,troubleshooting with india team 11/23 - Change the query with the column char2
66 | 2023-11-20 | "#69 - From Adoption tracker PCO Full view data - not showing missing data, only Matched data displaying in the panel" | Total row coun is 241K and dashboard is not showing correct data. Need to modified the query to display missing items | Dipesh
67 | 2023-11-20 | Dashboard documentation of ARES GRN Reconciliation |  | Sujan |  |  |  | 11/20 - No access to sharepoint to add dashboard details
68 | 2023-11-22 | Worker Node high resource cosumption | Elastic data node was consuming high resource | Dipesh |  |  | Completed | 11/22 - Due to data ingestion in elastic there was the hign resource consumption
68 | 2023-11-22 | ECOM OMS ILS Dashboard | Schedule query/create datapipeline and dashboard in UAT | Sujan |  |  | Completed | 11/23- Dashboard created and waiting for validation 11/23 - NULL value in ECOM details panel. Need to modify query
69 | 2023-11-22 | GRN Monitoring Queries | Add 'Header Level Missing GRN' - should use als_obs_ils_rms_grn_header_vw and replace by Missing GRN Details that is already in dashboard (Detailed Level Discrepancies) | Sujan | 2023-11-22 |  | Completed | 11/23- Qeury modification and dashboard fixes
70 | 2023-11-23 | RMS-ARES Item Reconcilation | added a new panel to represent count of items by country | sujan | 2023-11-23 |  | completed | 11/23 Query scheduling, data pipelines and Dashboard creation.
71 | 2023-11-23 | Query changes for all ECOM header panels in ECOM dashboard | header panel for Ecom Dashboard are updated | Sujan | 2023-11-23 |  | completed
72 | 2023-11-23 | Dashboard fixes for Adjustment monitoring and pco monitoring | changed query and dashboard fixes in prod after call with alshaya ITops Team | Dipesh | 2023-11-23 |  | completed | 11/24 - data count for pco monitoring is not matching with db and elastic
73 | 2023-11-24 | Added ECOM ILS KPI % in Ecom dashboard | scheduling query, data pipeline and dashboard creation | Sujan | 2023-11-24 |  | completed
74 | 2023-11-24 | updated query timing fot PCO monitoring | query and data pipelines to run at 11 30 | Dipesh | 2023-11-24 |  | completed
75 | 2023-11-24 | ECOM OMS Dashboard | header level panel fixed but in detail level panel we are facing issue due to null. updated query | Dipesh | 2023-11-29 |  | complete | 11/27- replaced -999 with null valur and finalized the dashboard for validation 11/29 - ECOM OMS-RMS dashboard completed. 11/30- ECOM OMS-ILS Dashboard completed. 12/08 - Reload Dashboard in PROD
76 | 2023-11-27 | Ecom OMS RESA Dashboard | scheduling metricbeat, data pipelines and dashboard creation | sujan |  |  | in progress | 11/30- updated query to be shared by team. 12/05 - updated resa query for sales header view .[added control to show data based on brand ] 12-8- Updated query for sales detail view in UAT. 12/11 - Updated the sales detail view panel Dashboard finalised and submitted for validation
77 | 2023-11-27 | Dasboard fixes for RMS-ARES item Reconcilation | query change and panel changes | Sujan | 2023-11-27 |  | complete | validated
78 | 2023-11-28 | Query modification and dashboard modification for RMS-GRN Dashboard in Prod |  | Sujan | 2023-11-28 |  | complete | validated
80 | 2023-11-29 | PROD ISSUE | cluster down because of heavy ram and cpu usage. | Dipesh/Sujan | 2023-11-30 | 1 |  | increased cpu and ram for better performance. the cluster is stable now.
79 | 2023-11-30 | Deployment of RMS-ARES ITEM recon in PROD | Data pipelines, Dashboard in Prod | Dipesh | 30-N0v-23 |  | complete
80 | 2023-11-30 | Prod Dashboard fixes | Dashboard modification for 3Pl GRN , GRN monitoring and ASN monitoring | Sujan | 2023-11-30 |  | complete
81 | 2023-12-01 | HB_HEN DASHBOARD | Scheduling queries and data pipeline in UAT | Sujan |  |  | Completed | 12/6 : the query need to be modified. waiting for updated qiery.
82 | 2023-12-04 | POC on Stock recon | since the data were high and resulted max bucket error, trying to solve it with another approch. seperate query for all warehouse. control to filter out warehouse , research on tabbed approach | Sujan/ Dipesh |  |  | Completed | controls is being used for now.
83 | 2023-12-05 | Prod dashboard fixes | Adding Filter [ today ] in all 3pl and monitoring dashboard | Sujan | 2023-12-05 |  | Completed | 12/13 - Reverting back this changes in all monitoring dashboard
84 | 2023-12-07 | Prod Deployment of ECOM OMS RMS RECON | scheduling queries and data pipelines , import export of Dashboard from UAT TO PROD | Sujan | 2023-12-07 |  | Completed | 12-08 - Reloading queries in PROD
85 | 2023-12-07 | ECOM Intra Picks Country Dashboard | scdeluing queries , data pipelines and dashboard in UAT | Dipesh | 2023-12-07 |  | Completed | 12-8 - line graph and table data are not matching, troubleshooting 12/14 Dashboard validated and deployed to PROD
86 | 2023-12-12 | ECOM RESA PROD DEPLOYMENT | scheduling queries and data pipelines , import export of Dashboard from UAT TO PROD | sujan | 2023-12-12 |  | Completed
87 | 2023-12-13 | Dashboard Documentation | Updating recent deployed Dashboard in PROD | sujan | 2023-12-14 |  | Completed
88 | 2023-12-15 | Unrealised Sales Metric Views | scdeluing queries , data pipelines and dashboard in UAT | sujan | 2023-12-07 |  | Completed
89 | 2023-12-15 | Elastic pod autoscaling |  | Dipesh |  |  | In progress | 1/5 - Call with logic internal team podautoscaling review 1/5- Research on elastic multiple data nodes architecture
90
91
92
93 | 2024-01-05 | Data mismatch in Unrealized sales oms ares details dashboad | Data in oms ares ageing in days not matchin wih database | Sabil |  | 1 | In progress | 1/5 - Create template for the column but still elastic is taking data as long but the type should be float
94 | 2024-01-08 | Separation of the the blocks of monitoring and 3PL from items.yml | Creating a separate file for these dashboard to avoid any errors as these need frequenty modification. | Nabin | 2024-01-08 | 1 | Completed | Files are separated and ready after the creation of the pipeline
95